## Slide 1
This material was produced under grant number SH-22316-SH-1 from the Occupational Safety and Health Administration, U.S. Department of Labor. It does not necessarily reflect the views or policies of the U.S. Department of Labor, nor does mention of trade names, commercial products, or organizations imply endorsement by the U.S. Government.
Quick Wins 5S and 8 Wastes
Presented By The University of Texas-School of Public Health

## Slide 2: Learning Objectives
By the end of this module participants should be able to:
Identify the value of a quick win
Identify the principles of 5S
Select the appropriate strategies to apply the 5S approach in the hospital unit environment.
Describe the 8 types of wastes
Analyze the 8 wastes in the hospital unit environment.

## Slide 3: The DMAIC Process with Tools
Define
Measure
Analyze
Improve
Control
3&4
Phase
Tools:
FMEA
Quick Wins 5S & The 8 Wastes
DAY 2

## Slide 4: Value of a Quick Win
It is easy to achieve
Gives a project a jumpstart to help build momentum
Offers a team a rallying point
Builds confidence of team members

## Slide 5: What is 5S?
Purpose:
To create and maintain an organized, clean, safe and high performing workplace.
  Enables anyone to distinguish between normal and abnormal conditions at a glance
  A systematic way to improve workplace and processes through frontline staff involvement

## Slide 6: Example of 5S
After:
Before:

## Slide 7
ORT
TRAIGHTEN (Set in Order)
CRUB
TANDARDIZE
The Principles of 5 S
USTAIN
S
S
S
S
S

## Slide 8
MAY 1996
JUNE 1996
JULY 1996
5 S Steps
traighten
(Set in Order)
S
ort
S
crub
S
tandardize
S
ustain
S

## Slide 9: An Orderly Environment
An orderly environment consists of three things:
  Evaluation of the usefulness of all things located within the physical space, and elimination of all that is not useful
  Organization of the useful items so they are always within reach and easily found when needed
  A workplace that is clean and neat at all times
Benefits of an orderly environment
  Elimination of wasted space
  Improved productivity
  Enhanced morale

## Slide 10: The First S:
Organization improves work flow; this will have a huge impact on Productivity and Quality
Organization also helps improve communication; it communicates visually
Determine what is needed and remove the rest.
ORT
S

## Slide 11: Red Tag Method
Establish rules for distinguishing between what is and is not needed
Identify needed and unneeded items and attach Red Tags to all potentially unneeded items. Write specific reason for Red Tagging and sign and date each tag
Remove Red Tag items and temporarily store them in an identified holding area
Sort through Red Tag items; dispose of those which are truly superfluous. Other items can be eliminated at an agreed upon interval when it is clear that they have no use. Ensure that all stakeholders agree
Determine ways to improve the workplace so that unnecessary items do not accumulate
Continue to Red Tag regularly

## Slide 12
The Second S:
Make a place for everything and label items for easy recovery.
TRAIGHTEN (Set in Order)
S

## Slide 13
Definition
  Keeping areas clean on a continual basis
Why
  A clean workplace is indicative of a quality product and process
  Dust and dirt cause product contamination and potential health hazards
  Helps to identify abnormal conditions
The Third S:
CRUB
S

## Slide 14
Standardize and make the orderly condition routine
This photo is a 5S checklist, which spells out the tasks needed to maintain the area
Without standardization, conditions will go back to their prior state
The Fourth S: TANDARDIZE
S
- Sample Form -

## Slide 15
Definition
To maintain our discipline, we need to
practice and repeat until it becomes a
way of life
Why
To build 5-S’s into our every day process
Things to Remember
  Develop schedules, check lists
  Good habits are hard to break
  Commitment and discipline toward housekeeping is essential in taking the first step in being world class
The Fifth S: USTAIN
S

## Slide 16
The Fifth S: USTAIN
S

## Slide 17
The Fifth S: USTAIN
S

## Slide 18
The Fifth S: USTAIN
S

## Slide 19
THE 5S OBSERVATION SUMMARY
SHIFT: AREA:
Two noted 5S successes:
Score Results:
Current situation Score:
Desired situation Score:
Five priority areas needing attention:
1
2
3
4
5
5S target objective:
/4
/4
The Fifth S: USTAIN
S

## Slide 20
5S Levels Of Achievement
Sort
Straighten
Standardize
Scrub
Sustain
Needed and not
needed items are
mixed throughout
the area.
Items are randomly
placed throughout
the workplace.
Key area items
checked are not
identified and are
unmarked.
Work area methods
are not always
followed and are
not documented.
Work area checks
are randomly done
and there is no
5S measurement.
4
Continuous
Improvement
3
Focus On
Reliability
2
Make It Visual
1
Focus On
Basics
0
Just Beginning
Level
Necessary and un-
necessary items are
identified; those not
needed are gone.
Needed items are
safely stored and
organized according
to usage frequency.
Key area items
are marked to check
and required level of
performance noted.
Work group has
documented area
arrangement and
controls.
Initial 5S level
is established and
and is posted in
the area.
Initial cleaning is
done and mess
sources are known
and corrected.
Needed items are
outlined, dedicated
locations are labeled
in planned quantities.
Visual controls and
indicators are set
and marked for
work area.
Agreements on
labeling, quantities,
and controls are
documented.
Work group is
routinely checking
area to maintain
5S agreements.
Cleaning schedules
and responsibilities
are documented
and followed.
Minimal needed
items arranged in
manner based on
retrieval frequency.
Work area cleaning,
inspection, and
supply restocking
done daily.
Proven methods for
area arrangement
and practices are
used in the area.
Sources, frequency
of problems are
noted w/ root cause
and corrective action.
Cleanliness problem
areas are identified
and mess prevention
actions are in place.
Needed items can
be retrieved in 30
seconds with
minimum steps.
Potential problems
are identified and
countermeasures
documented.
Proven methods for
area arrangement
and practices are
shared and used.
Root causes are
eliminated and
improvement actions
include prevention.
Notes: Handout for learners

## Slide 21: Why is Value Stream Mapping important for assessing current state?
After:
Before:

## Slide 22
Doing more than you need to – within a process
It just doesn’t meet expectations
Excess movement-person/material – within a process
Shipping stuff to different locations
Things just don’t happen when they should
Keeping stuff on-hand when it isn’t required
Doing more than you need to – Output of a process
Extra Processing
Defects
Motion
Transportation
Waiting
Excess Inventory
Overproduction
Non-Utilized Human Intellect
Not including the input of those people most directly involved in the process
The 8 Wastes
D
O
W
N
T
I
M
E
Wastes
The simple explanation…

## Slide 23
The 8 Wastes in Detail
1. DEFECTS
Repair of a product or service to fulfill customer requirements
Scrap
Warranty
Customer returns
2. OVERPRODUCTION
Producing more than needed (beyond customer demand)
Producing faster or sooner than needed
Visible as stored material
Result of producing to speculative demand (forecast)

## Slide 24
The 8 Wastes in Detail
3. WAITING
Idle time that results when dependent activities are not fully synchronized
Waiting for a machine to process or a machine waiting for an operator to load
4. NON-UTILIZED HUMAN INTELLECT
Not listening to employees ideas who are involved first hand in the actual work
Not incorporating front line workers in the process of new product design
Not acting on employee complaints about legitimate problems and solutions

## Slide 25
The 8 Wastes in Detail
5. TRANSPORTATION
Any material movement or handling
Transportation does not add value and should be minimized or eliminated
6. INVENTORY
Excessive in-process or finished goods inventory caused by large lot production or processes with long Cycle Times
Inventory should exist for two reasons:
  Buffer required to maintain throughput in an
  environment where variation is present
  Satisfy customer demand
Reducing variation enables inventory reduction

## Slide 26
The 8 Wastes in Detail
7. MOTION
Any movement of people or machines which does not contribute added value to the product or service
  Programming delay times
  Excessive walking distance between operations
  Ergonomically inefficient motion
8. EXTRA PROCESSING
Effort which adds no value to a product or service
Enhancements which are “invisible” to the customer
Work which could be combined with another process

## Slide 27: Exercise # 1: The 8 Wastes
Notes: Provide the worksheets for the participants

## Slide 28: Summary
Quick wins 5S is to create and maintain an organized, clean, safe and high performing workplace.
The Principles of 5 S :
  Sort
  Straighten
  Scrub
  Standardize
  Sustain
The 8 Wastes in Detail:
  Defects
  Overproduction
  Waiting
  Non-Utilized Human Intellect
  Transportation
  Excess Inventory
  Motion
  Extra Processing

## Slide 29: Thank You